## Sheet1
VDI Data Center Budget
Planning
Description | Man-Hour Labor | Cost/Man-Hour | Labor Cost | Material Cost | Total
Requirements | 200 | 40 | 8000 |  | 8000
Design and Engineering - Civil | 160 | 75 | 12000 |  | 12000
Design and Engineering - Electrical | 160 | 75 | 12000 |  | 12000
Design and Engineering - Mechanical | 160 | 75 | 12000 |  | 12000
Design and Engineering - Networking | 120 | 60 | 7200 |  | 7200
Design and Engineering - IT | 80 | 60 | 4800 |  | 4800
Disaster Recovery Plan | 80 | 50 | 4000 |  | 4000
Planning Total | 960 |  | 60000 | 0 | 60000
Procurement
Description | Man-Hour Labor | Cost/Man-Hour | Labor Cost | Material Cost | Total
RFP Development and Initiation | 80 | 35 | 2800 |  | 2800
RFP Submission and Evaluation | 80 | 35 | 2800 |  | 2800
Contractors Assignment | 80 | 35 | 2800 |  | 2800
Procurement Total | 240 |  | 8400 | 0 | 8400
Construction
Description | Man-Hour Labor | Cost/Man-Hour | Labor Cost | Contract or Equipment Cost | Total
Site Preperation | 40 | 25 | 1000 | 5000 | 6000
Site Construction - Civil | SUBCONTRACTED |  |  | 180000 | 180000
Site Construction - Electrical | SUBCONTRACTED |  |  | 1000000 | 1000000
Site Construction - Mechanical | SUBCONTRACTED |  |  | 250000 | 250000
Site Construction - Networking | 120 | 35 | 4200 | 25000 | 29200
Site Construction - IT | 160 | 35 | 5600 | 200000 | 205600
Construction Total | 320 |  | 10800 | 1660000 | 1670800
Testing and Commissioning
Description | Man-Hour Labor | Cost/Man-Hour | Labor Cost | Material Cost | Total
Data Center Testing | 120 | 50 | 6000 | 2000 | 8000
Acceptence Testing | 40 | 50 | 2000 |  | 2000
Testing and Commissioning Total | 160 |  | 8000 | 2000 | 10000
Migration
Description | Man-Hour Labor | Cost/Man-Hour | Labor Cost | Material Cost | Total
Prepare Migration Plan | 40 | 50 | 2000 |  | 2000
Execute Migration | 280 | 35 | 9800 |  | 9800
Migration Total | 320 |  | 11800 | 0 | 11800
Project Management
Description | Man-Hour Labor | Cost/Man-Hour | Labor Cost | Material Cost | Total
Determen Member of Management Consultant Team | 40 | 50 | 2000 |  | 2000
Project Management | 1720 | 120 | 206400 |  | 206400
Project Coordination | 800 | 35 | 28000 |  | 28000
Prepare Acceptence Report | 80 | 50 | 4000 |  | 4000
Project Managemen Total | 2640 |  | 236400 | 0 | 240400
Project Subtotal | 4640 |  | 335400 | 1662000 | 2001400
Project Total
Description | Man-Hour Labor |  | Labor Cost | Contract, Equipment, or Material Cost | Total
Project Contingency (5%) |  |  |  |  | 100070
Project Total | 4640 |  | 335400 | 1662000 | 2101470